## Slide 1: Project Timeline
April | May | June | July | August
Conduct analysis of market and WCC-provided data |  |  |  | 
Administer information-gathering surveys to students, faculty, staff, and community members |  |  |  | 
Conduct interviews and focus groups with internal constituents, including students, faculty, and staff |  |  |  | 
 | Develop and finalize a vision statement based on input from the WCC community |  |  | 
 |  | Conduct prioritization workshop and produce draft plan outline |  | 
 |  | Facilitate community focus groups by sector |  | 
 |  |  |  | Conduct community forum and town hall
 |  |  |  | Finalize draft strategic plan
After the Strategic Plan is finalized, Phase 4 of the project will commence with the development of the Strategic Enrollment Management (SEM), Continuous Improvement, and Technology operational plans to be completed by early 2025.
v
Help to coordinate outreach to priority external constituents
Provide feedback on Vision Statement versions in June
Next Steps for the Board
June Board Meeting
The Board can expect updates on:
Emerging vision, priorities, and initiatives
= Strategic Plan Development
= Constituent Engagement
Key